## 00 Readme
Field | Value
Document | Draft UAT Resource Collection Next Gen
Date | 2026-09-24
Environment | Supabase DEV vvojshgcduqlugngpzkj
Purpose | Validasi penerimaan bisnis Auth, Access Management, workflow claim, master, report, timetable, log, dan People Performance.
In scope | RC Next Gen pada Supabase DEV, termasuk People Performance, registrasi upload, claim workflow, report, dashboard publik, dan ekspor.
Out of scope | Migrasi penuh Document Center, Print Document, parser Upload_CB legacy, sinkronisasi 15 menit, cutover produksi, dan load/stress test sebelum staging tersedia.
Execution rule | Gunakan data sintetis untuk mutasi. Jangan menghapus atau mengubah data operasional.
Result values | Not Run / In Progress / Pass / Fail / Blocked
Evidence | Simpan screenshot, request ID, batch ID, nomor dokumen, response API, atau hasil query.
Exit criteria | Semua P0/P1 PASS, tidak ada blocker/critical terbuka, evidence lengkap, dan batas yang belum diuji dicatat.
Known limitations | Browser UAT nyata, screenshot klik, Vercel redeploy, staging, dan load test belum dibuktikan.
References | docs/PRD-Resource-Collection.md; docs/rc-release-2026-09-24.md; docs/rc-user-upload-approval.md; docs/rc-testing-status.md

## 01 Test Cases
ID | Area | Priority | Scenario | Precondition | Steps | Expected Result | Actual Result | Status | Evidence / Reference | Defect ID
AUTH-01 | Auth | P0 | Login User ID dan PIN valid | Akun aktif tersedia | Buka login; masukkan User ID dan PIN; submit | Sesi dibuat dan profil sesuai scope terbaca
AUTH-02 | Auth | P1 | Login dengan variasi casing User ID | Akun legacy tersedia | Uji casing asli lalu uppercase/lowercase | Fallback hanya pada invalid credential; rate limit/network error tidak diulang
AUTH-03 | Auth | P0 | PIN salah | Akun aktif tersedia | Masukkan PIN salah | Login ditolak tanpa membocorkan informasi sensitif
AUTH-04 | Auth | P0 | Akun Pending, Rejected, atau nonaktif | Akun fixture tersedia | Login dengan tiap status | Tidak mendapat data bisnis dan pesan status jelas
AUTH-05 | Auth | P0 | PIN awal wajib diganti | Akun baru/fixture must_change_password | Login lalu buka modul bisnis | Bootstrap bisnis ditahan sampai PIN berubah
AUTH-06 | Auth | P1 | PIN mengandung spasi | Akun test tersedia | Login atau ubah PIN dengan spasi | Nilai diproses sesuai aturan dan tidak dipangkas diam-diam
AUTH-07 | Auth | P1 | Logout dan reload | Sesi aktif | Logout; reload halaman | Sesi/cache dibersihkan dan halaman meminta login
AUTH-08 | Auth | P1 | Session expired | Sesi dapat dibuat expired | Akses modul setelah token expired | Pengguna diarahkan login ulang tanpa data parsial
ACCESS-01 | Access | P0 | Katalog role System Manager | Login sebagai System Manager | Buka Registrasi/Edit Akses | Delapan role tersedia
ACCESS-02 | Access | P0 | Supervisor tidak dapat memilih System Manager | Login sebagai Supervisor | Buka form role dan kirim payload manipulasi | Opsi tidak tersedia dan server menolak payload
ACCESS-03 | Access | P0 | Depot di luar scope | User dengan scope terbatas | Pilih atau kirim depot lain | Tidak ditawarkan dan tetap ditolak server
ACCESS-04 | Access | P0 | Registrasi manual valid | Manager berwenang dan data valid | Isi form; submit; refresh daftar | Auth, profil, mapping, ledger, audit atomik; akun muncul setelah refresh
ACCESS-05 | Access | P0 | Klik Buat Akun dua kali | Form valid | Klik dua kali cepat | Satu akun dan satu transaksi
ACCESS-06 | Access | P0 | Retry request ID sama | Request pertama sukses | Kirim ulang request ID/payload sama | Replay mengembalikan akun yang sama
ACCESS-07 | Access | P0 | Request ID sama payload berbeda | Request pertama sudah ada | Kirim payload berbeda | Ditolak sebagai konflik
ACCESS-08 | Access | P0 | Requester role/depot dimanipulasi | User non-manager atau scope terbatas | Ubah payload browser lalu submit | Server tidak mempercayai nilai browser
ACCESS-09 | Access | P0 | Reviewer menyetujui request sendiri | Request milik reviewer tersedia | Reviewer mencoba approve | Ditolak
ACCESS-10 | Access | P1 | Viewer membuka Access Management | User hanya punya viewer | Buka, cari, refresh, create/update | Read berhasil sesuai scope; mutasi ditolak
ACCESS-11 | Access | P1 | Edit akses sebagian field | User aktif tersedia | Kirim hanya sebagian field | Field yang tidak dikirim tetap dipertahankan
ACCESS-12 | Access | P0 | Perubahan role membersihkan mapping | User memiliki mapping lama | Ubah role lalu baca ulang akses | Mapping/region tidak relevan dibersihkan
USER-UP-01 | User Upload | P1 | Download template user | Manager berwenang | Download template | Tujuh kolom sesuai spesifikasi
USER-UP-02 | User Upload | P0 | Upload file valid | File <=500 baris | Pilih file; buka preview | Identitas, role, depot asal, dan semua area terlihat
USER-UP-03 | User Upload | P0 | Upload >500 user | File 501 baris | Upload file | Ditolak; tidak dipotong diam-diam
USER-UP-04 | User Upload | P1 | PIN invalid atau nama terlalu panjang | File fixture invalid | Preview file | Baris ditolak dengan alasan jelas
USER-UP-05 | User Upload | P0 | Ajukan upload | Preview valid | Klik Ajukan Approval | Status Pending; belum ada grant efektif
USER-UP-06 | User Upload | P0 | Approve upload | Proposal Pending dan reviewer berwenang | Buka Approval Request; approve | Profil aktif, suffix dibuat, area diterapkan
USER-UP-07 | User Upload | P0 | Reject upload | Proposal Pending | Reject proposal | Akun tetap tidak aktif tanpa grant
USER-UP-08 | User Upload | P0 | Retry upload | Request yang sama pernah diajukan | Klik Retry Gagal | Tidak membuat duplikat atau mengganti PIN
USER-UP-09 | User Upload | P0 | PIN tidak bocor | Proposal dan audit tersedia | Periksa preview, proposal, log | PIN tidak tampil atau tersimpan
USER-UP-10 | User Upload | P0 | Supervisor upload System Manager | Login Supervisor | Upload role System Manager | Ditolak
CLAIM-UP-01 | Claim Upload | P0 | Preview dan submit satu claim | Claim Not Yet valid | Pilih dokumen; preview; submit | Menjadi Submitted; versi, history, audit tercatat
CLAIM-UP-02 | Claim Upload | P0 | Submit batch valid | Batch <=500 item | Upload/submit batch | Semua item sukses sesuai limit
CLAIM-UP-03 | Claim Upload | P0 | Batch >500 item | Batch 501 item | Submit batch | Ditolak tanpa silent truncation
CLAIM-UP-04 | Claim Upload | P0 | Duplikat dalam file | File berisi duplikat | Preview dan submit | Duplikat ditandai; tidak ada transaksi ganda
CLAIM-UP-05 | Claim Upload | P0 | Versi usang | Claim sudah berubah | Submit versi lama | Ditolak stale version
CLAIM-UP-06 | Claim Upload | P1 | Leading zero | Data rekening/customer/KTP/NPWP berawalan nol | Upload dan baca detail | Nilai tetap teks dan tidak kehilangan nol
CLAIM-UP-07 | Claim Upload | P0 | Tanggal invalid/ambigu | File tanggal invalid | Preview dan submit | Ditolak; sistem tidak menebak tanggal
CLAIM-UP-08 | Claim Upload | P0 | Jenis cashback | Campaign Transfer, CN, Rebate, RA07/RA7, Voucher | Submit tiap jenis | Resolver dan workflow sesuai aturan masing-masing
CLAIM-UP-09 | Claim Upload | P0 | Transfer tanpa rekening | Claim Transfer tanpa rekening | Submit | Ditolak sesuai validasi
CLAIM-UP-10 | Claim Upload | P0 | Retry submit | Request ID sama | Kirim dua kali | Tidak menggandakan claim/history
APPROVAL-01 | Approval | P0 | Approve submit normal | Item Submitted pending | Approve | Submitted menjadi Approved
APPROVAL-02 | Approval | P0 | Reject submit normal | Item Submitted pending | Reject | Kembali Not Yet dan dapat diajukan ulang
APPROVAL-03 | Approval | P0 | Approve Rebate | Item Rebate Submitted | Approve lalu proses | Approved -> Bulk Process -> Done
APPROVAL-04 | Approval | P0 | Approve Rebate Manual RA07/RA7 | Item Rebate Manual | Approve | Menjadi Done; tahap approval dan done tercatat
APPROVAL-05 | Approval | P0 | Hold dari Upload | Claim aktif | Ajukan Hold; approve/reject | Status efektif berubah hanya setelah approve
APPROVAL-06 | Approval | P0 | Expired dari Upload | Claim aktif | Ajukan Expired; approve/reject | Efektif hanya setelah approve
APPROVAL-07 | Approval | P0 | Item sudah diputuskan | Item sudah approved/rejected | Buka antrean | Tidak muncul sebagai pending
FLOW-01 | Workflow | P0 | Transfer/CN normal | Data dan permission lengkap | Submit; approve; release; claim; clearing | Not Yet -> Submitted -> Approved -> Released -> Claimed -> Done
FLOW-02 | Workflow | P0 | Rebate | Data dan permission lengkap | Submit; approve; bulk process | Not Yet -> Submitted -> Approved -> Bulk Process -> Done
FLOW-03 | Workflow | P0 | Expired Claim Process | Claim Released/Claimed valid | Post Expired | Langsung Expired tanpa approval tambahan
FLOW-04 | Workflow | P0 | Release sebelum approval | Claim Submitted | Coba release | Ditolak
FLOW-05 | Workflow | P0 | Claim sebelum Released | Claim Approved | Coba claim | Ditolak
FLOW-06 | Workflow | P0 | Clearing sebelum Claimed | Claim Released | Coba clearing | Ditolak
FLOW-07 | Workflow | P0 | Dua user update versi sama | Dua sesi membuka claim sama | Submit bersamaan | Satu sukses; lainnya konflik versi
FLOW-08 | Workflow | P0 | Rollback batch | Batch dengan satu item invalid | Commit batch | Seluruh batch rollback
FLOW-09 | Workflow | P1 | Gross-up dan rounding | Fixture nilai batas tersedia | Proses dan bandingkan expected | Rumus dan pembulatan sesuai contoh disetujui
MASTER-01 | Master | P1 | Customer lintas depot | Customer di depot lain | Cari customer | Tidak terlihat
MASTER-02 | Master | P1 | Campaign periode/status | Campaign aktif, archived, beda periode | Buka claim/report | Resolver hanya memakai campaign yang sesuai
MASTER-03 | Master | P1 | Depot Master | User berwenang | Buka Key Master Depot | Code, nama, region, alamat, link konsisten
MASTER-04 | Master | P1 | Profil depot request | User berwenang | Ajukan perubahan alamat/email/grade | Masuk approval; nilai efektif berubah setelah reviewer lain approve
MASTER-05 | Master | P1 | Approve request sendiri | Request dibuat user yang sama | Coba approve | Ditolak
REPORT-01 | Report | P0 | Filter server-side | User memiliki beberapa depot | Filter depot/region/campaign | Hasil hanya sesuai filter dan scope
REPORT-02 | Report | P1 | Status grouping | Data tiap status tersedia | Buka Report | Pending Depot/OSC/Finance sesuai definisi
REPORT-03 | Report | P1 | Nominal kartu dan detail | Data nominal tersedia | Bandingkan kartu, detail, ekspor | Kartu memakai jt; detail/ekspor rupiah penuh tanpa pecahan
REPORT-04 | Report | P1 | Tanggal/timezone | Data boundary UTC/Jakarta | Buka report dan detail | Tampilan Asia/Jakarta; tanggal dd-Mmm-yyyy; timestamp lengkap
REPORT-05 | Report | P0 | CSV export | Report terfilter | Ekspor CSV | Header/filter/timezone konsisten; formula dinetralkan
REPORT-06 | Report | P0 | Dashboard publik | Akses URL publik | Buka dashboard dan periksa response | Hanya agregat; tidak ada data sensitif/detail akun
OPS-01 | Timetable | P1 | Timetable sesuai scope | User memiliki depot terbatas | Buka dan filter timetable | Hanya depot/region berwenang
OPS-02 | Timetable | P1 | Klasifikasi timetable | Fixture Not Yet/Compiled/Completed/Not Achieved | Buka matrix | Klasifikasi dan persentase sesuai data
OPS-03 | Timetable | P0 | Unknown historis | Claim history tidak tercatat | Buka histori | Unknown, bukan Not Yet
OPS-04 | Log | P1 | Log Activity | Transaksi sudah dilakukan | Buka log | Aktor, entitas, modul, stage, batch, waktu tersedia
OPS-05 | Log | P0 | Filter log authorization | User scope terbatas | Manipulasi filter | Tidak memperluas otorisasi
PEOPLE-01 | People | P0 | Tab OSC | User punya permission dan data OSC | Buka People Performance > OSC | Supervisor terkait dan depot yang ditangani tampil
PEOPLE-02 | People | P0 | Tab Supervisor | Supervisor punya OSC binaan | Buka tab Supervisor | OSC aktif dan jumlah depot tampil
PEOPLE-03 | People | P0 | Irisan yurisdiksi | User punya relasi lintas scope | Buka detail | Hanya irisan assignment dan yurisdiksi pembaca
PEOPLE-04 | People | P0 | Depot unik | Satu depot muncul melalui beberapa relasi | Buka summary | Depot dihitung sekali
PEOPLE-05 | People | P1 | Claim metrics | Fixture berbagai status | Buka Details | Total, stage, persentase, status asli sesuai scope
PEOPLE-06 | People | P1 | Timetable metrics | Fixture tiap klasifikasi | Buka Details | Not Yet, Compiled, Completed, Not Achieved, Unknown benar
PEOPLE-07 | People | P0 | History harian | Claim history tersedia | Pilih grain day dan tanggal | Rows dan processed sesuai akhir hari bisnis
PEOPLE-08 | People | P1 | History mingguan/bulanan | History tersedia | Pilih grain week/month | Tanggal awal/akhir dan metrics benar
PEOPLE-09 | People | P0 | Range 366 hari | User berwenang | Pilih range 366 hari | Diterima
PEOPLE-10 | People | P0 | Range >366/future/terbalik | User berwenang | Kirim range invalid | Ditolak dengan pesan validasi
PEOPLE-11 | People | P0 | Role invalid | User berwenang | Panggil role selain osc/supervisor | Ditolak
PEOPLE-12 | People | P0 | User di luar yurisdiksi | User lain di depot berbeda | Buka history/detail | Ditolak
PEOPLE-13 | People | P0 | Archived depot/campaign | Data archived tersedia | Buka summary | Tidak masuk metrics
PEOPLE-14 | People | P1 | Refresh route | Frontend tersedia | Buka /people-performance lalu refresh | Rute tetap bekerja dan scope tidak berubah
SEC-01 | Security | P0 | Anonymous akses tabel/RPC | Tidak login | Panggil endpoint | Ditolak
SEC-02 | Security | P0 | HTML/script injection | Fixture nama/campaign/log berisi markup | Tampilkan detail/log | Dirender sebagai teks
SEC-03 | Security | P0 | Sensitive data leakage | Data rekening/KTP/NPWP tersedia | Periksa dashboard publik/log/export | Tidak muncul di jalur yang tidak berizin
SEC-04 | Security | P0 | Supervisor lintas depot | Supervisor scope terbatas | Baca/mutasi depot lain | Ditolak server
UX-01 | UX | P1 | Desktop workflow | Browser desktop | Jalankan login sampai report | Tidak ada layout, modal, chart, atau tabel rusak
UX-02 | UX | P1 | Mobile workflow | Browser mobile | Jalankan login, filter, detail, submit | Tidak ada overlap/overflow kritis
UX-03 | UX | P1 | Error/loading/empty | Siapkan kondisi error dan data kosong | Buka tiap state | State dibedakan jelas
UX-04 | UX | P1 | Double submit UI | Form valid | Klik tombol berulang | Pengiriman kedua ditahan
NFR-01 | NFR | P0 | No production mutation | Environment DEV dan fixture | Jalankan seluruh UAT | Tidak ada data bisnis terhapus/terubah tanpa evidence
NFR-02 | NFR | P1 | Audit traceability | Transaksi berhasil | Cari request ID/actor/history | Setiap keputusan dapat ditelusuri
NFR-03 | NFR | P1 | Performance disclaimer | Tidak ada staging | Review hasil | Tidak ada klaim lulus load 1.000/1.500 users

## 02 Test Data
Data ID | Jenis | Nilai / Deskripsi | Tujuan | Owner | Status
TD-01 | Akun | System Manager aktif | Scope global dan approval | UAT Owner | Disiapkan
TD-02 | Akun | Supervisor scope terbatas | Yurisdiksi dan People Performance | UAT Owner | Disiapkan
TD-03 | Akun | OSC aktif dengan depot assignment | Tab OSC dan approval | Business Tester | Disiapkan
TD-04 | Akun | Viewer tanpa permission mutasi | Uji read-only | Business Tester | Disiapkan
TD-05 | Claim | Transfer, CN, Rebate, RA07/RA7, Voucher | Uji seluruh workflow | Business Tester | Disiapkan
TD-06 | Claim | Status Not Yet sampai Done/Expired | Uji status dan grouping | Business Tester | Disiapkan
TD-07 | People | Supervisor -> OSC -> beberapa depot | Uji mapping dan depot unik | UAT Owner | Disiapkan
TD-08 | People | History Unknown dan range 366 hari | Uji history | UAT Owner | Disiapkan
TD-09 | Upload | Valid, duplikat, 501 baris, PIN invalid | Uji preview/limit | Business Tester | Disiapkan
TD-10 | Security | Nama/campaign/log dengan HTML/script | Uji escaping | Security Reviewer | Disiapkan

## 03 Defect Log
Defect ID | Found Date | Test Case ID | Severity | Description | Environment | Owner | Status | Target Fix | Retest Result
DEF-001 |  |  | Critical |  | DEV |  | Open
DEF-002 |  |  | High |  | DEV |  | Open
DEF-003 |  |  | Medium |  | DEV |  | Open

## 04 Sign-off
Area | Business Owner | Tester | Execution Date | Result | Open Defect IDs | Evidence Link | Approval / Signature | Notes
Auth & Session |  |  |  | Not Run
Access Management & Registrasi |  |  |  | Not Run
Claim Upload & Approval |  |  |  | Not Run
Workflow Release/Claim/Clearing |  |  |  | Not Run
Master Data & Profil Depot |  |  |  | Not Run
Report/Analytics/Dashboard/Export |  |  |  | Not Run
Timetable & Log Activity |  |  |  | Not Run
People Performance |  |  |  | Not Run
Security & Data Privacy |  |  |  | Not Run
Visual Desktop/Mobile |  |  |  | Not Run
Overall Go / No-Go |  |  |  | Not Run